## Sheet1
|  | Project Internal |  |  |  | Assessment / Advice organization
|  | Project team preparation |  |  |  | XYZ |  |  | Architecture |  | XYZ | [9 empty] | XYZ
Decision document | Responsible | Tractor / preparer | % ready | Review Projectmng | Delivered for review | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized | anonymized
2. Lifecycle users LMS | Anonymized | Anonymized | 90% | Y | Y | Y | N | N | Y | Y | Y | Y | Y | Y | Y | N | Y | Y | N | Y | N | N | N | n/a | Y
4. Accessibility design | Anonymized | Anonymized | lapses | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | N
5. User roles and rights within LMS | Anonymized | Anonymized | lapses | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
7. Use Learning Object Respoitory (canvas commons) | Anonymized | Anonymized | 100% | Y | Y | Y | N | Y | Y | Y | Y | N | N | N | Y | N | N | Y | N | Y | Y | Y | Y | n/a
8. Personal Schedule | Anonymized | Anonymized | 100% | N | N | Y | N | Y | Y | Y | Y | Y | N | Y | N | N | N | N | N | Y | Y | N | Y | n/a
9. Policy for cross-year subjects (communities) | Anonymized | Anonymized | 100% | N | N | Y | N | N | Y | Y | Y | N | N | N | N | N | N | N | N | N | N | Y | N | n/a
12. Governance libraries | Anonymized | Anonymized | 100% | N | N | Y | Y | N | Y | Y | Y | Y | N | N | Y | Y | Y | Y | Y | Y | Y | N | Y | n/a
13. Partial mark registration | Anonymized | Anonymized | lapses | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
15. Notifications | Anonymized | Anonymized | 80% | N | N | Y | N | N | Y | Y | Y | N | N | N | N | Y | Y | N | N | Y | Y | Y | N | n/a
18. Archiving policy | Anonymized | Anonymized | lapses | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
19. Policy support Blackboard and Canvas | Anonymized | Anonymized | lapses | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
21. Portfolio | Anonymized | Anonymized | 100% | Y | Y | Y | N | Y | Y | Y | Y | N | N | N | N | N | N | N | N | N | Y | Y | Y | n/a
24. Naming of subjects | Anonymized | Anonymized | lapses | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
27. Development decisions | Anonymized | Anonymized | lapses | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a